## Summary
| Total |  |  | Coding |  |  | Meetings
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Damon | 11900 | 4850 | 7050 | 9800 | 1500 | 8300 | 1000 | 2050 | -1050
Kiran | 10600 | 3250 | 7350 | 8500 | 1300 | 7200 | 1000 | 950 | 50
Max | 10000 | 6950 | 3050 | 7900 | 3400 | 4500 | 1000 | 2050 | -1050
Dylan | 7200 | 7500 | -300 | 6000 | 6000 | 0 | 1000 | 1300 | -300
Graeme | 6900 | 4950 | 1950 | 5400 | 3300 | 2100 | 1000 | 1250 | -250
Marry | 8500 | 2300 | 6200 | 7100 | 1300 | 5800 | 1000 | 500 | 500
Total | 55100 | 29800 | 25300 | 44700 | 16800 | 27900 | 6000 | 8100 | -2100
Systems Analysis
[10 empty] | Budgeted | Actual | Deficit
[10 empty] | 1100 | 1300 | -200
[10 empty] | 1100 | 1000 | 100
[10 empty] | 1100 | 1500 | -400
[10 empty] | 200 | 200 | 0
[10 empty] | 500 | 400 | 100
[10 empty] | 400 | 500 | -100
[10 empty] | 4400 | 4900 | -500

## Gantt
| Predicted Hours | Hours Committed | Key |  | Complete |  |  | Active |  |  | Planned
Damon |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Unity/C# Resarch and Training | 15 | 10 | bar: 3 to Complete 9
Asset Research | 4 | 3 | bar: 3
Design Class Heirachy | 5 | 5 | bar: 3 to Complete 6
Implement Basic Class Heirarchy | 8 | 4 | bar: Complete 9 to Active 15
Implement Basic Component Heirarchy | 8 | 4 | bar: Complete 9 to Complete 12
Implement Basic Behaviors | 10 | 7 | bar: Active 18 to Active 21
Implement AI Component | 10 | 3 | bar: Active 18 to Active 21
Implement Adv. Behaviors | 15 | 15 | bar: Active 18 to Planned 30
Test Components and Behaviors | 15 | 12 | bar: Planned 33 to Planned 45
Test AI Component | 5 | 10 | bar: Planned 33 to Planned 42
Fix Merging Issues | 3 | 15 | bar: 3 to Active 15
Total | 98 | 88 | bar: 3 to Active 15
Kiran |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Unity Training | 15 | 6 | bar: 3 to 15
Indentifying Game Manager Requirements | 5 | 3 | bar: 3
Camera Control | 8 | 1
Game State Control | 6 | bar: 3 to 6
Loading components in Game Scene | 4 | bar: 9 to 12
Managing Game Stats | 6
Design Save/Load features | 10 | bar: 9 to 15
Programming | 15 | 1
Testing | 12 | 2
Documentation | 4 | bar: 3
Total | 85 | 13
Max |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Player Creation | 5 | 5 | bar: 3
Input Mapping | 2 | 1
Collisions | 6 | 1 | bar: 6 to 9
Movement design | 4 | 4 | bar: 12
Attack design | 4 | 0 | bar: 15
Skill tree design | 5 | 0 | bar: 18
Programming | 10 | 11 | bar: 21 to 24
Testing | 40 | 11 | bar: 27 to 78
Documentation | 3 | 1 | bar: 27 to 30
Total | 79 | 34
Dylan |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Determine necessary HUD elements | 3 | 4 | bar: 3
Design HUD | 6 | 6 | bar: 6 to 9
Design Menus | 6 | 3 | bar: 12 to 15
Implement Menus | 9 | 12 | bar: 18 to 24
Implement HUD Classes | 9 | 11 | bar: 27 to 33
Implement HUD | 12 | 9 | bar: 36 to 45
Integrate Sound | 9 | 0 | bar: 48 to 54
Testing | 6 | 15 | bar: 57 to 60
Total | 60 | 60
Graeme |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
World generation by noise | 18 | 18 | bar: 3 to 18
Generation in chunks | 9 | 6 | bar: 21 to 27
Implementation of biomes | 9 | 2 | bar: 30 to 36
Testing for realisticness | 6 | 1 | bar: 39 to 42
Testing | 6 | 4 | bar: 45 to 48
Documentation | 3 | 1 | bar: 51
Integration | 3 | 1 | bar: 54
Total | 54 | 33
Mary |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Design classes | 1 | 1
Coding Base Classes | 2 | 0.5 | bar: 3
Coding Sub Classes | 5 | 5.5 | bar: 6 to 9
Integrating classes with player | 6 | 2 | bar: 6 to 9
Variable coordination | 1 | 1 | bar: 6
Data structures (for Powerup types) | 3 | 2 | bar: 6
Adding physics | 3 | 0.25 | bar: 6
Increasing level difficulty integration algorithms | 5 | 2 | bar: 12 to 15
Dynamic creation algorithms | 5 | 0.75 | bar: 12 to 15
Testing Object functionality | 3 | 2 | bar: 18
Testing Object generation | 5 | 3 | bar: 18 to 21
Timeout functions | 6 | 5 | bar: 6 to 9
Separate player stat functionality | 2 | 0.25 | bar: 6
Documentation | 3 | 3 | bar: 24
Installation | 3 | bar: 24
Research | 14 | 0.5 | bar: 3 to 12
Artwork | 4 | 13 | bar: 3 to 6
Total | 71 | 41.75
Group
Total Hours | 447 | 269.75
Total Cost | 44700 | 26975

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 20 | Oct. 11 | Nov. 10
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Re-Planning | Minimum Viable Product | Test Code Integrateion
| Hours | 1.5 | 4 | 2 | 2 | 3 | 8
Damon | 20.5
Kiran | 9.5
Max | 20.5
Dylan | 13
Graeme | 12.5
Mary | 5
Total | 81 | 6 | 16 | 8 | 10 | 15 | 32